## Basic Eucalyptus
No. | Section | Test Description | Procedure | Pass Critera | PASS/FAIL | Comments
1 | Services (admin) | Ensure all eucalyptus services are reporting correct status information | euca-describe-services | All services are either in ENABLED or DISABLED state
2 |  | Ensure there is available cloud resources | euca-describle-availability-zones verbose | Each "Free" column item for each instance type should be non-zero
3 | Images (admin) | List all images available in the public image repository | eustore-describe-images | List of Eucalyptus managed images should be displayed
4 |  | Install a CentOS 6 image from the public repository | eustore eustore-install-image -i 3868652036 -b centos6 -k kvm | Output should display image downloading and bundling, uploading and registering to eucalyptus
5 |  | List all images in your eucalyptus cloud | euca-describe-images | List should include EKI, ERI and EMI from image imported in last step
6 |  | Make the images public (available to all cloud users) | for i in `euca-describe-images¦ awk '{print $2}'`; do euca-modify-image-attribute -l -a all $i; done | Command returned without error and image will be visible in later steps
7 | IAM (admin) | Create an account called testaccount | euare-accountcreate -a testaccount | Name of account returned and account ID number
8 |  | Create an access key for the admin user in the testaccount | euare-useraddkey --delegate testaccount -u admin | Access key and secret key returned
9 |  | Create a UI login profile for admin in testaccount | euare-useraddloginprofile -u admin -p test --delegate=testaccount | No command output, no error listed
10 |  | Create x509 certificates for admin user in testaccount | euare-usercreatecert -u admin --delegate=testaccount | Public and Private x509 certificates displayed
11 |  | List accounts | euare-accountlist | List of accounts should include testaccount
12 |  | Download credentials for testaccount | euca-get-credentials -a testaccount -u admin test-account-creds.zip | No output, test-account-creds.zip should exist in current working directory
13 |  | Uncompress test account credentials | unzip test-account-creds.zip | Output should show zip file decompressing and list of files
14 |  | Source test account credentials to environment | source eucarc | No output, but "env ¦ grep EC2" should list some environment variables that are set
15 | Keypair | Create an ssh keypair to be used when accessing an instance | euca-add-keypair test-key > test-key | Key is created successfully with private key residing in ~/test-key file
16 |  | List keypairs | euca-describe-keypairs | List of keypairs should be displayed with "test-key" in output
17 |  | Change permission on test key for use with ssh client | chmod 400 test-key | Permissions on file should change so only owner has read access
18 | Security Groups | Create a security group with a custom description | euca-create-group -d "testgroup" testgroup | Group successfully created, no error message
19 |  | List groups | euca-describe-groups | Groups should be listed with testgroup in the output
20 |  | Add a security group setting for ssh access | euca-authorize -P tcp -p 22 -s 0.0.0.0/0 testgroup | Output should show the permissions added in EC2 format
21 |  | Add a security group setting for icmp ping | euca-authorize -P icmp -t -1:-1 -s 0.0.0.0/0 testgroup | Output should show the permissions added in EC2 format
22 | Images | List all public images | euca-describe-images | This should list the CentOS 6 EKI, ERI and EMI
23 | Instances | Run 5 instances and ensure all instance can run | euca-run-instances -k test-key -g testgroup -n 5 emi-XXXXXXXX | Output should show instance-id allocation for all instances and all pending
24 |  | After 3 minutes check to see if all instances are running | euca-describe-instances | All instances should be in 'running' mode. If some are still pending, wait another 3 minutes before marking test as failed
25 |  | Choose one instance and send a icmp ping to it | ping <HOSTNAME> | Ping replies should be recieved
26 |  | Connect to an instance via ssh | ssh -i test-key root@<HOSTNAME> | Ssh client should connect into an instance and you should be displayed with a command line prompt
27 | Volumes | Create a 10gb volume (repeat for each zone) | euca-create-volume -z <ZONE> -s 10 | Command should return volume ID and status creating
28 |  | List volumes | euca-describe-volumes | volume ID from above should be listed with status available
29 |  | Attach volume to an instance | euca-attach-volume -i <INSTANCE-ID> -d /dev/vdb <VOLUME-ID> | Command should return volume ID
30 |  | Check attachment by connecting to instance and creating a file system on the device | ssh -i test-key root@<HOSTNAME>; mkfs.ext4 /dev/vdb | mkfs should successfully create a file system on the /dev/vdb device
31 |  | Detach volume from instance | euca-detach-volume <VOLUME-ID> | volume ID should be listed in output
32 | Snapshots | Create a snapshot of the 10gb test volume | euca-create-snapshot <VOLUME-ID> | Snapshot ID returned
33 |  | Check snapshot status, re-run command until snapshot has fully completed | euca-describe-snapshots | Snapshot from previous command listed and uploaded percentage will increase to 100%
34 | Clean-up | Terminate all instances | for i in `euca-describe-instances ¦ awk '/running/ {print $2}'`; do euca-terminate-instances $i; done | After a few minutes all instances should be in terminated state in "euca-describe-instances"
35 |  | Delete all snapshots | for i in `euca-describe-snapshots ¦ awk '{print $2}'`; do euca-delete-snapshot $i; done | After a minute "euca-describe-snapshots" should not list any snapshots
36 |  | Delete all volumes | for i in `euca-describe-volumes ¦ awk '{print $2}'`; do euca-delete-volume $i; done | After a minute "euca-describe-volumes" should not list any volumes
37 |  | Delete all security groups | euca-delete-group testgroup | "euca-describe-groups" should only list default group
38 |  | Delete all keypairs | euca-delete-keypair test-key | "euca-describe-keypairs" should not list any keypairs
39 |  | Remove testaccount | euare-accountdel -a testaccount | "euare-accountlist" should only list eucalyptus account

## HA
No. | Section | Test Description | Procedure | Pass Critera | PASS/FAIL | Comments
1 | CLC | Ability to run instances after CLC failover | Power off active CLC wait until DISABLED CLC has transitioned to ENABLED, launch an instance with users credentials | Secondary CLC should show ENABLED status in euca-describe-services. CLC powered off should show as NOTREADY. Users should be able to launch instances successfully
2 | CLC | Secondary CLC should rejoin a cloud after a reboot | Turn on CLC you powered off, watch euca-describe-services until the CLC starts in DISABLED mode | euca-describe-services should show the other service re-join the cloud in DISABLED mode within 5 minutes
3 | CLC | Reboot primary CLC to move service back to initial CLC | Reboot the ENABLED CLC. | DISABLED CLC should move back to ENABLED and other CLC should reboot and re-join and become DISABLED within 5 minutes
4 | CC | Ability to run instances after a CC failover | Power off active CC wait until DISABLED CC has transitioned to ENABLED, launch an instance with users credentials | Secondary CC should show ENABLED status in euca-describe-services. CC powered off should show as NOTREADY. Users should be able to launch instances successfully
5 | CC | Secondary CC should rejoin a cloud after a reboot | Turn on the CC you powered off, watch euca-describe-services until the CC starts in DISABLED mode | euca-describe-services should show the other CC re-join the cloud in DISABLED mode after 5 minutes
6 | CC | Check traffic failover when a CC fails | Ping a running instance on it's public IP. Reboot primary CC. | Ping should halt then resume as the secondary CC becomes ENABLED. CC that was rebooted should re-join the cloud after a few minutes and be DISABLED mode in euca-describe-services
7 | Walrus | Check walrus failover and service availability | Power off the ENABLED Walrus server, upload a new image to Eucalyptus and run it. | Secondary Walrus becomes ENABLED, images are uploaded correctly and Instance launches. Other walrus server becomes NOTREADY.
8 | Walrus | Check walrus failover and sync | Turn on powered off Walrus server, wait for it to boot and check it is available in DISABLED mode in euca-describe-services. Check to make sure DRBD syncs over the new image. | Walrus starts in DISABLED mode and image is synced across, check /proc/drbd for DRBD sync status.
9 | SC (SAN adapter only) | Ensure SC is not in the storage path | Create a volume. Attach volume to an instance. Reboot ENABLED SC. Interact with volume inside the instance | Secondary SC state should tranisiton to ENABLED and activity with the volume from inside the instance should not be affected.
10 | SC (SAN adapter only) | Fail back the SC service | Reboot ENABLED SC to failback SC service to previous system | Other SC should transition to ENABLED and rebooted SC should reboot and become DISABLED

## Network
No. | Section | Test Description | Procedure | Pass Critera | PASS/FAIL | Comments
1 | Physical Cabling & Bonding | Remove primary cable from each system in turn to test bonding configuration | Disconnect primary connection to system. Monitor "/proc/net/bonding/bondX" on each system. Ensure "euca-describe-services". Repeat for multiple bonds | Each server fails over to its secondary interface without affecting cloud services. If test fails check bonding configuration and cabling configuration.
2 |  | Replace primary cable to each system to restore network bonding | Replace primary connection to each system. Monitor "/proc/net/bonding/bondX" on each system. | Each server detects network reconnection and adds interface back to bond. If test fails check bonding configuration and cabling configuration.
3 |  | Remove secondary cable from each system in turn to test bonding configuration | Disconnect secondary connect to system. Monitor "/proc/net/bonding/bondX" on each system. Repeat for multiple bonds. | Each server fails over to its secondary interface without affecting cloud services. If test fails check bonding configuration and cabling configuration.
4 |  | Replace secondary cable to each system to restore network bonding | Replace primary connection to each system. Monitor "/proc/net/bonding/bondX" on each system. | Each server detects network reconnection and adds interface back to bond. If test fails check bonding configuration and cabling configuration.
5 | Network Switch | Turn off primary switch to test switch redundancy | Remove power cable from primary swtich. Monitor "/proc/net/bonding/bondX" on each system. | Each server should detect a link going down. If test fails check servers are correctly cabled to the switches.
6 |  | Turn on primary switch to test switch redundancy | Replace power cable to primary switch. Monitor "/proc/net/bonding/bondX" on each system. | Each server should detect link coming up and add the interface back to the bond.
7 |  | Turn off secondary switch to test switch redundancy | Remove power cable from secondary swtich. Monitor "/proc/net/bonding/bondX" on each system. | Each server should detect a link going down. If test fails check servers are correctly cabled to the switches.
8 |  | Turn on secondary switch to test switch redundancy | Replace power cable to secondary switch. Monitor "/proc/net/bonding/bondX" on each system. | Each server should detect link coming up and add the interface back to the bond.